## Timeline
Milestone/Task | Owner | Week 1 (04 - 08 Jan) | Week 2 (11 - 15 Jan) | Week 3 (18 - 22 Jan) | Week 4 (25 - 29 Jan) | Week 5 (25 - 29 Jan) | Week 6 (1 - 5 Feb)
Initial understanding, analysis, knowledge gain | Team | [6 empty] | Legend
User Interface | [8 empty] | On Track
Setup initial web interface | Raina, Priyanka | [7 empty] | Completed
Create HH Consumption chart | Raina | [7 empty] | Extended
Create GDP chart | Priyanka | [7 empty] | Delayed
Create Ethnicity by Gender chart | Raina | [7 empty] | Holiday
Create State population chart | Priyanka
Create Literacy rate by State chart | Raina | [6 empty] | Trainee 1 | Raina Kishor
Create State wise per capita income chart | Priyanka | [6 empty] | Trainee 2 | Priyanka Koparkar
Filter and driving UI | Aishwarya, Jayneeta | [6 empty] | Trainee 3 | Aishwarya Naidu
Service integration | Raina, Priyanka | [6 empty] | Trainee 4 | Jayneeta Sinha
Integration Testing | Raina, Priyanka | [6 empty] | Trainee 5 | Akshat Shukla
Data Acquisition | [7 empty] | Jayneeta | Shubham Patil
Create Data Model | Aishwarya, Jayneeta
Import Data to MySQL | Aishwarya, Jayneeta
Data analysis SQL | Aishwarya, Jayneeta
Data Validation | Aishwarya, Jayneeta
Service Layer
Setup initial services model | Shubham, Akshat
Analysis 1 - HH Consumption | Shubham
Analysis 2 - GDP | Akshat
Analysis 3 - Ethnicity by Gender | Shubham
Analysis 4 - State Population | Akshat
Analysis 3 - Literacy rate by state | Shubham
Analysis 3 - Per capita income by state | Akshat
Integration Testing and validation | Shubham, Akshat

## Sheet2
Legend
| On Track | Trainee1 | Raina Kishor
| Completed | Trainee2 | Jayneeta Sinha
| Extended | Trainee3 | Akshat Shukla
| Delayed | Trainee4 | Priyanka Koparkar
| Holiday | Trainee5 | Shubham Patil
|  | Trainee6 | Aishwarya Naidu